ROCA PLATFORM AWS WELL-ARCHITECTED FRAMEWORK REVIEW

ROCA Unified Remediation Roadmap

AWS Well-Architected Framework Review (All 8 Flows)

Consolidated Cross-Batch Remediation Strategy for All 8 ROCA Flows

| Date | August 2026 |
| --- | --- |
| Version | 1.0 |
| Status | APPROVED |
| Classification | Engineering Leadership / Internal |
| Scope | All 8 ROCA Flows ¦ 4 Review Batches ¦ 6 AWS Well-Architected Pillars |
| Total Findings | ~60+ architectural gaps ¦ ~240-280 engineering days |

This document is the engineering leadership decision record for ROCA platform remediation investment.

Synthesized and de-duplicated from all 4 AWS Well-Architected Review batches.

# 1. Executive Summary

The ROCA platform AWS Well-Architected Framework Review was conducted across four batches covering all 8 application flows. This unified roadmap synthesizes and de-duplicates findings from all four batches into a single prioritized remediation strategy for engineering leadership decision-making.

OVERALL RISK POSTURE: HIGH Security: HIGH ¦ Reliability: HIGH ¦ Operational Excellence: MEDIUM ¦ Performance: MEDIUM Six systemic gaps compound across all 4 batches and all 8 flows. Immediate platform-wide action required.

## 1.1 Review Scope and Findings Volume

Across all 8 ROCA flows and 4 review batches, the Well-Architected reviews surfaced approximately 60+ architectural gaps totaling 240-280 engineering days of remediation effort. The findings span all six AWS Well-Architected pillars:

| Pillar | Findings | Critical | High | Medium | Low |
| --- | --- | --- | --- | --- | --- |
| Security | 15 | 8 | 4 | 3 | 0 |
| Reliability | 14 | 6 | 5 | 3 | 0 |
| Oper. Excellence | 13 | 3 | 6 | 4 | 0 |
| Perf. Efficiency | 12 | 1 | 5 | 5 | 1 |
| Cost Optimization | 9 | 0 | 1 | 4 | 4 |
| Sustainability | 7 | 0 | 0 | 5 | 2 |
| TOTAL | 70 | 18 | 21 | 24 | 7 |

## 1.2 Six Systemic Gaps — The Platform Risk Multipliers

The Batch 4 cross-batch analysis confirmed that Security and Reliability carry the highest concentration of critical gaps, driven by 6 systemic issues that have compounded across every batch. These 6 gaps appeared in all 4 review batches with escalating severity:

- Missing AWS WAF: No Web Application Firewall on any API Gateway stage. Escalated from High (Batch 1) to Critical (Batch 2+) when payment flows were assessed. Affects all 8 flows.

- Missing Amazon GuardDuty: No account-level threat detection for Lambda, RDS, S3, or API Gateway. Critical finding across all batches.

- No Dead Letter Queues (DLQs): Silent data loss on async Lambda invocations and SQS queues across onboarding, payments, notifications, and scripture delivery. Critical across all 4 batches.

- JWT Token Rotation Without PKCE: Single most persistent security vulnerability. Affects every API endpoint across all 8 flows. Critical since Batch 1.

- Embedded State Machines: Onboarding, volunteer scheduling, event registration, and reading plan orchestration all use application-code state machines instead of AWS Step Functions. High across all batches.

- No EventBridge Custom Event Bus: Cross-flow communication relies on direct service-to-service calls, creating tight coupling. High across all batches, no centralized event schema or retry strategy.

## 1.3 Platform-First Remediation Strategy

The recommended strategy is platform-first remediation: implementing WAF, DLQs, GuardDuty, and JWT rotation as CDK/SAM templates in Phase 1 retroactively closes approximately 40% of all findings across the entire platform without flow-by-flow rework. Each platform-level fix is a force-multiplier that simultaneously reduces risk across all 8 flows.

Key Investment Insight Completing Phase 1 (5 items, ~14 engineering days) retroactively closes ~40% of all 70+ findings. The Phase 1 CDK/SAM templates apply automatically to every current and future ROCA flow, providing the highest ROI of any remediation investment. Total program: ~240-280 engineering days across 20 weeks.

## 1.4 Total Effort Summary

| Phase | Timeline | Effort | Items | Priority |
| --- | --- | --- | --- | --- |
| Phase 1: Platform-Wide Critical | Weeks 1-4 | ~14 days | 5 items | Critical |
| Phase 2: Flow-Specific Critical | Weeks 5-10 | ~45 days | 7 items | High |
| Phase 3: Architectural Improvements | Weeks 11-16 | ~50 days | 7 items | Medium |
| Phase 4: Optimization & Observability | Weeks 17-20 | ~30 days | 9 items | Low |
| TOTAL | 20 weeks | ~240-280 days | 28 items | — |

# 2. Flow-to-Batch Mapping

The following table maps all 8 ROCA application flows to their respective Well-Architected review batches and identifies the dominant architectural theme assessed in each batch.

| # | Flow Name | Batch | Review Date | Dominant Theme | Key Risk Areas | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | New Member Onboarding | Batch 1 | Q1 2026 | Identity & Access Security | JWT rotation, state machines, DLQs, WAF, GuardDuty | Done |
| 2 | Event Creation (6-step wizard) | Batch 2 | Q1 2026 | Payment Security & PCI DSS | Stripe integration, RRULE parsing, Secrets Manager | Done |
| 3 | Event Discovery & RSVP | Batch 2 | Q1 2026 | Concurrency & Capacity Control | RSVP race conditions, waitlist ordering, capacity gates | Done |
| 4 | Volunteer Assignment & Scheduling | Batch 3 | Q2 2026 | Orchestration Complexity | Auto-schedule algorithm, swap workflows, saga pattern | Done |
| 5 | Event Cancellation & Notification | Batch 3 | Q2 2026 | Cascade Saga Reliability | Refund saga, notification cascade, SQS FIFO ordering | Done |
| 6 | Recurring Event Management | Batch 3 | Q2 2026 | RRULE & DST Correctness | RFC 5545 parsing, DST drift, bounded expansion | Done |
| 7 | Push Notification Engagement | Batch 3 | Q2 2026 | Delivery Reliability | SES bounce handling, FCM HTTP v1, multi-channel delivery | Done |
| 8 | Scripture & Lectionary Management | Batch 4 | Q2 2026 | Third-Party API Resilience | Bible API circuit breaker, offline sync, search indexing | Done |

Note: Batch 2 produced 3 separate reports (initial findings, gap analysis, payment security assessment) as findings emerged during review. All Batch 2 reports are consolidated in this unified roadmap.

# 3. Platform Risk Summary — Six Persistent Critical Gaps

The following table documents the 6 systemic architectural gaps that have persisted across all 4 review batches. Each gap appears in multiple flows and compounds in severity as new flows expose additional attack surfaces and failure modes. Severity trend arrows indicate cross-batch escalation.

| # | Gap | B1 | B2 | B3 | B4 | Trend | AWS Service Fix |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Missing AWS WAF on API Gateway | High | Critical | Critical | Critical | ↗ Escalated | AWS WAF + ACL |
| 2 | Missing Amazon GuardDuty | High | Critical | Critical | Critical | ↗ Escalated | GuardDuty + RDS/Lambda Protection |
| 3 | No Dead Letter Queues (DLQs) | Critical | Critical | Critical | Critical | → Sustained | SQS DLQs + Lambda on-failure destinations |
| 4 | JWT Rotation Without PKCE | Critical | Critical | Critical | Critical | → Sustained | Cognito + PKCE + JWKS validation |
| 5 | Embedded State Machines (not Step Functions) | Critical | High | High | High | ↓ Improving | Step Functions Standard + Express |
| 6 | No EventBridge Custom Event Bus | High | High | High | High | → Sustained | EventBridge + Schema Registry + Pipes |

Severity Trend Key: ↗ Escalated = severity increased across batches  |  → Sustained = same severity across all batches  |  ↓ Improving = severity reduced in later batches

# 4. Phase 1: Platform-Wide Critical (Weeks 1–4, ~14 Engineering Days)

Impact: Completing Phase 1 retroactively closes ~40% of all findings across the entire platform These 5 items must be codified as CDK/SAM templates and enforced via AWS Config rules so they apply to every current and future ROCA flow automatically. Estimated sprint: 14 engineering days with 2 engineers.

| # | Item & Description | AWS Service | Days | Batches | AWS Config Rule | Priority |
| --- | --- | --- | --- | --- | --- | --- |
| P1-1 | Deploy WAF on all API Gateway stages AWSManagedRulesCommonRuleSet + ACFP. Protects all endpoints against SQL injection, XSS, bot abuse. PCI DSS v4.0 requirement for payment flows. | AWS WAF (WebACL) | 3-4 | 1, 2, 3, 4 | api-gw-associated-with-waf | Critical |
| P1-2 | Enable GuardDuty Platform-Wide Account-level threat detection for Lambda, RDS, S3, API Gateway. Enable RDS Protection and Lambda Protection add-ons. | Amazon GuardDuty | 1 | 1, 2, 3, 4 | guardduty-enabled-centralized | Critical |
| P1-3 | Add DLQs on All Async Lambda Invocations SQS DLQs + Lambda on-failure destinations + CloudWatch Alarms. Prevents silent data loss across onboarding, payments, notifications, scripture delivery. | SQS DLQs + CloudWatch | 3 | 1, 2, 3, 4 | lambda-dlq-check | Critical |
| P1-4 | JWT Refresh Token Rotation with PKCE Closes the single most persistent vulnerability affecting every API endpoint across all 8 flows. Cognito refresh rotation + PKCE + JWKS validation. | Amazon Cognito | 5 | 1, 2, 3, 4 | Custom Config Rule | Critical |
| P1-5 | Stripe Webhook Signature Verification HMAC-SHA256 validation of all payment webhooks via Stripe constructEvent(). Idempotency keys on all POST payment requests. CloudTrail audit logging. | Stripe SDK + CloudTrail | 2 | 2 | N/A | Critical |

## 4.1 CDK/SAM Template Deployment Strategy

Phase 1 items must be delivered as reusable CDK constructs or SAM templates that can be applied to every API Gateway stage simultaneously. The recommended implementation order within Phase 1:

- Day 1: GuardDuty enablement (1 day, zero-risk activation, immediate threat visibility)

- Days 2-4: DLQ configuration on all async Lambdas (CDK construct parameterized by function ARN)

- Days 5-7: WAF WebACL creation and attachment to all API Gateway stages

- Days 8-12: JWT rotation and PKCE implementation in Cognito User Pool

- Days 13-14: Stripe webhook signature verification and idempotency keys

The CDK constructs should be stored in a shared platform library and imported by each flow's CDK stack. AWS Config rules should be deployed in the same Phase 1 sprint to provide continuous compliance monitoring after initial deployment.

# 5. Phase 2: Flow-Specific Critical (Weeks 5–10, ~45 Engineering Days)

Phase 2 addresses flow-specific critical and high-priority findings that require targeted engineering work. These items build on the platform foundations established in Phase 1 and address the most significant reliability and correctness risks in individual flows.

| # | Item & Description | Flow(s) | AWS Service | Days | Dependency | Phase | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- |
| P2-1 | RSVP Atomic Capacity Control SELECT FOR UPDATE SKIP LOCKED + Redis atomic DECR fast-path gate. Eliminates lost-update race conditions for concurrent RSVPs. | Flow 3 (B2) | PostgreSQL + Redis | 10 | P1-3 DLQs | Phase 2 | Critical |
| P2-2 | Event Cancellation Saga Orchestration Compensating transactions for notification → refund → reassignment cascade. Step Functions Standard with Stripe idempotency keys. | Flows 2,5 (B2,B3) | Step Functions Standard | 10 | P1-3 DLQs, P1-5 Stripe | Phase 2 | Critical |
| P2-3 | SES Bounce & Complaint Handling Separate SNS topics for bounces/complaints. Maintain bounce rate <5%, complaint <0.1%. FCM HTTP v1 migration (legacy API deprecated May 2024). | Flow 7 (B3) | SES + SNS + FCM v1 | 5 | P1-3 DLQs | Phase 2 | Critical |
| P2-4 | Bible API Circuit Breaker Lambda Powertools circuit breaker with DynamoDB-backed CLOSED/OPEN/HALF_OPEN state per provider (ESV API + Bible.api independent). 5,000 req/day ESV cap mitigation. | Flow 8 (B4) | Lambda Powertools + DynamoDB + Redis | 5 | P1-3 DLQs | Phase 2 | Critical |
| P2-5 | RRULE Library Fixes (DST + Bounds) DST drift correction with Luxon post-processing. Prefer COUNT over UNTIL. Enforce bounded expansion (90-day window). PostgreSQL materialized instances. | Flows 2,6 (B2,B3) | rrule.js + Luxon + PostgreSQL | 10 | None | Phase 2 | High |
| P2-6 | Stripe API Keys to Secrets Manager KMS encryption, automatic 90-day rotation, least-privilege IAM. Removes hardcoded/env-var API key anti-pattern. Required for PCI DSS v4.0 compliance. | Flow 2 (B2) | Secrets Manager + KMS | 3 | P1-4 JWT | Phase 2 | High |
| P2-7 | SQS FIFO for Ordered Operations FIFO queues for waitlist promotion and cancellation cascade ordering. Message group IDs by eventId ensure deterministic processing order. | Flows 3,5 (B2,B3) | SQS FIFO Queues | 3-4 | P1-3 DLQs | Phase 2 | High |

## 5.1 Phase 2 Implementation Notes

- P2-1 & P2-2 (RSVP + Cancellation Saga): These two items are the most complex in Phase 2. Allocate dedicated engineers with Step Functions and distributed transaction experience. The saga pattern requires careful design of compensating transactions before coding begins.

- P2-3 (SES Bounce Handling): FCM HTTP v1 migration is time-sensitive. The legacy Firebase Cloud Messaging API was deprecated May 2024. Failure to migrate will result in push notification delivery failures.

- P2-4 (Bible API Circuit Breaker): Lambda Powertools is recommended over Step Functions-based circuit breaker for this use case due to simplicity. Track ESV API and Bible.api failure states independently in DynamoDB.

- P2-5 (RRULE): DST boundary testing is critical. Create test cases for the spring-forward and fall-back boundaries in all US timezones. The 90-day bounded expansion cap prevents runaway materialization.

# 6. Phase 3: Architectural Improvements (Weeks 11–16, ~50 Engineering Days)

Phase 3 addresses architectural uplift items that require significant design work. These items build the long-term platform foundations needed for scaling, resilience, and maintainability. Completing Phase 3 transforms the ROCA architecture from ad-hoc to Well-Architected-compliant.

| # | Item & Description | Flow(s) | AWS Service | Days | Dependency | Phase | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- |
| P3-1 | Step Functions Migration (All Embedded State Machines) Migrate onboarding, volunteer assignment, recurring events, notification delivery, reading plans from application-code state machines to Step Functions Standard + Express (nested). | All (B1-B4) | Step Functions Std + Express | 20 | P1-3 DLQs, P2-2 Saga | Phase 3 | High |
| P3-2 | EventBridge Custom Event Bus Cross-flow decoupling with domain events: member.approved, event.cancelled, reading.completed. EventBridge Pipes + Schema Registry for type safety. | All (B1-B4) | EventBridge + Pipes + Schema Registry | 5 | P3-1 Step Functions | Phase 3 | High |
| P3-3 | RDS Proxy Deployment Connection pooling for Lambda-to-PostgreSQL. Prevents connection exhaustion during traffic spikes (Sunday morning concurrent reads). Alert at 80% connection utilization. | Flows 2,8 (B2,B4) | RDS Proxy | 3 | VPC config | Phase 3 | High |
| P3-4 | PostgreSQL GIN Index Optimization GIN indexes on tsvector columns for event search and scripture search. AWS benchmarks show ~5,000x improvement (5,882ms → 1.14ms on 5M rows). fastupdate + gin_pending_list_limit tuning. | Flows 2,8 (B2,B4) | PostgreSQL GIN Indexes | 3 | None | Phase 3 | High |
| P3-5 | KMS Encryption for PII Data Per-classification KMS keys for family/address data and Bible API credentials. Separate CMKs for PII vs. payment data vs. spiritual data. Key rotation every 365 days. | Flows 1,8 (B1,B4) | KMS + Secrets Manager | 3 | P2-6 Secrets Mgr | Phase 3 | High |
| P3-6 | AppSync Offline Sync Migration Replace last-write-wins with AWS AppSync Optimistic Concurrency + Delta Sync. Amplify DataStore for automatic offline support. Resolves concurrent lectionary editing conflicts. | Flow 8 (B4) | AWS AppSync + Amplify DataStore | 8 | Schema design | Phase 3 | High |
| P3-7 | Row-Level Security (RLS) Policies PostgreSQL RLS for multi-tenant lectionary isolation and custom lectionary data. Prevents cross-tenant data contamination in lectionary_config and lectionary_readings tables. | Flows 8,1 (B4,B1) | PostgreSQL RLS | 3 | P3-5 KMS | Phase 3 | Medium |

# 7. Phase 4: Optimization & Observability (Weeks 17–20, ~30 Engineering Days)

Phase 4 delivers cost optimizations, performance improvements, and observability enhancements. These items have clear financial ROI and reduced risk profiles, making them suitable for the final sprint once the critical and architectural phases are complete.

| # | Item & Description | Flow(s) | AWS Service | Days | Cost Impact | Phase | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- |
| P4-1 | HTTP API Migration (from REST API) ~70% API cost reduction. HTTP API v2 supports JWT authorizers natively, WebSocket, and lower latency. Migration requires updating route integrations and authorization logic. | All (B1) | API Gateway HTTP API | 3 | -70% API cost | Phase 4 | Medium |
| P4-2 | Graviton2 (arm64) Lambda Migration ~20% cost/performance improvement across all Lambda functions. Use AWS Compute Optimizer to identify candidate functions. Right-size memory per function. | All (B3,B4) | Lambda arm64 + Compute Optimizer | 3 | -20% Lambda cost | Phase 4 | Medium |
| P4-3 | Redis Cache-Aside Pattern 30-60s TTLs for event search. 5-15 min for popular events. 24h for scripture text. ElastiCache Serverless with IAM auth. Replace KEYS with SCAN. Sub-ms response for cached hits. | Flows 2,8 (B2,B4) | ElastiCache Serverless | 4 | -60% DB read load | Phase 4 | Medium |
| P4-4 | X-Ray Distributed Tracing End-to-end observability across Lambda, API Gateway, and SQS flows via Lambda Powertools X-Ray integration. Enables automatic service map and cold start tracking. | All (B1-B4) | AWS X-Ray + Lambda Powertools | 4 | Observability +80% | Phase 4 | Medium |
| P4-5 | CloudFront API Caching + Origin Shield Cache event metadata and HLS audio segments. Separate cache behaviors: .m3u8 manifests (1-3s TTL) vs .ts segments (24h+ TTL, immutable). Origin Shield reduces origin hits. | Flows 2,8 (B2,B4) | CloudFront + Origin Shield | 3 | -40% origin requests | Phase 4 | Medium |
| P4-6 | Provisioned Concurrency for Critical Paths Eliminate cold-start latency on payment-critical and scripture-lookup paths. Use Application Auto Scaling to adjust provisioned concurrency based on predictable load patterns (Sunday mornings). | Flows 2,8 (B2,B4) | Lambda Provisioned Concurrency | 2 | p99 latency -60% | Phase 4 | Medium |
| P4-7 | Easter Computus Validation Suite Automated tests for years 2000-2100 against authoritative Easter date tables. Runtime guards for years outside validated range. Edge cases: March 22 (earliest) and April 25 (latest). | Flow 8 (B4) | Test framework + runtime guards | 3 | Bug prevention | Phase 4 | Medium |
| P4-8 | Data Lifecycle Policies S3 Intelligent-Tiering for media and audio. Archive old lectionary data (>3 cycles = 9 years) to Glacier. Archive completed/abandoned reading plans after configurable retention period. | Flows 2,8 (B2,B4) | S3 Intelligent-Tiering + Glacier | 2 | -30% storage cost | Phase 4 | Low |
| P4-9 | Reserved Instances + Savings Plans RDS Reserved Instances (up to 72% savings vs. On-Demand), ElastiCache RIs, Lambda Compute Savings Plans (up to 17%). Requires 12-24 month baseline usage data. | All flows | RDS RI + Compute Savings Plans | 2 | Up to -72% RDS cost | Phase 4 | Low |

# 8. Severity Distribution by Pillar

The following table provides the complete breakdown of all architectural findings by AWS Well-Architected pillar and severity level, aggregated across all 4 batches and 8 flows.

| Well-Architected Pillar | Critical | High | Medium | Low | Total | Risk Level |
| --- | --- | --- | --- | --- | --- | --- |
| Security | 8 | 4 | 3 | 0 | 15 | Critical |
| Reliability | 6 | 5 | 3 | 0 | 14 | Critical |
| Operational Excellence | 3 | 6 | 4 | 0 | 13 | High |
| Performance Efficiency | 1 | 5 | 5 | 1 | 12 | High |
| Cost Optimization | 0 | 1 | 4 | 4 | 9 | Medium |
| Sustainability | 0 | 0 | 5 | 2 | 7 | Low |
| TOTAL | 18 | 21 | 24 | 7 | 70 | HIGH |

## 8.1 Key Observations from Severity Distribution

- Security dominates Critical findings (8 of 18 total Criticals): WAF absence, GuardDuty absence, JWT rotation, Stripe webhook verification, and missing Secrets Manager for API keys account for all Security Criticals.

- Reliability Criticals are infrastructure-level: All 6 Reliability Criticals stem from missing DLQs, absent circuit breakers, and lack of saga orchestration — none require flow redesign, only infrastructure additions.

- No Cost Optimization Criticals: All cost findings are Medium or Low priority, confirming the platform functions at acceptable cost but has significant optimization headroom (est. 35-50% total cost reduction achievable via Phases 3-4).

- Sustainability baseline is healthy: Serverless-first architecture inherently maximizes utilization. All sustainability findings are Medium/Low and primarily relate to right-sizing and data lifecycle management.

# 9. Cross-Batch Consolidated Findings

The following table provides the complete consolidated remediation item list from all 4 batches, de-duplicated and normalized across all 8 flows. Items with the same root cause appearing in multiple batches have been merged into a single remediation item with all affected flows noted.

| ID | Description | Flow(s) | AWS Service | Days | Priority | Pillar | Phase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| P1-1 | Deploy WAF WebACL on all API Gateway stages (AWSManagedRulesCommonRuleSet + ACFP + rate limiting) | All 8 flows | AWS WAF | 3-4 | Critical | Security | Phase 1 |
| P1-2 | Enable GuardDuty with RDS Protection + Lambda Protection add-ons account-wide | All 8 flows | GuardDuty | 1 | Critical | Security | Phase 1 |
| P1-3 | Add SQS DLQs on all async Lambda invocations + on-failure destinations + CloudWatch Alarms | All 8 flows | SQS + Lambda | 3 | Critical | Reliability | Phase 1 |
| P1-4 | Implement JWT refresh token rotation + PKCE + JWKS validation via Amazon Cognito | All 8 flows | Cognito | 5 | Critical | Security | Phase 1 |
| P1-5 | Stripe webhook HMAC-SHA256 verification via constructEvent() + idempotency keys | Flow 2 (B2) | Stripe SDK | 2 | Critical | Security | Phase 1 |
| P2-1 | RSVP atomic capacity control: SELECT FOR UPDATE SKIP LOCKED + Redis atomic DECR gate | Flow 3 (B2) | PostgreSQL + Redis | 10 | Critical | Reliability | Phase 2 |
| P2-2 | Event cancellation saga: compensating transactions for notification-refund-reassignment cascade | Flows 2,5 | Step Functions | 10 | Critical | Reliability | Phase 2 |
| P2-3 | SES bounce/complaint handling: SNS topics, <5% bounce rate, <0.1% complaint, FCM HTTP v1 | Flow 7 (B3) | SES + SNS + FCM | 5 | Critical | Reliability | Phase 2 |
| P2-4 | Bible API circuit breaker: Lambda Powertools + DynamoDB CLOSED/OPEN/HALF_OPEN per provider | Flow 8 (B4) | Powertools + DynamoDB | 5 | Critical | Reliability | Phase 2 |
| P2-5 | RRULE DST drift correction with Luxon + COUNT over UNTIL + 90-day bounded expansion | Flows 2,6 | rrule.js + Luxon | 10 | High | Reliability | Phase 2 |
| P2-6 | Migrate Stripe API keys to Secrets Manager with KMS + 90-day rotation + least-privilege IAM | Flow 2 (B2) | Secrets Mgr + KMS | 3 | High | Security | Phase 2 |
| P2-7 | SQS FIFO queues for waitlist promotion and cancellation cascade (messageGroupId = eventId) | Flows 3,5 | SQS FIFO | 3-4 | High | Reliability | Phase 2 |
| P3-1 | Migrate all embedded state machines to Step Functions Standard + Express (nested workflows) | All flows | Step Functions | 20 | High | Oper. Exc. | Phase 3 |
| P3-2 | Deploy EventBridge custom event bus + Schema Registry + Pipes for cross-flow domain events | All flows | EventBridge | 5 | High | Oper. Exc. | Phase 3 |
| P3-3 | Deploy RDS Proxy for Lambda connection pooling; alert at 80% connection utilization | Flows 2,8 | RDS Proxy | 3 | High | Perf. Eff. | Phase 3 |
| P3-4 | Create GIN indexes on all tsvector columns (event search + scripture search) with fastupdate tuning | Flows 2,8 | PostgreSQL GIN | 3 | High | Perf. Eff. | Phase 3 |
| P3-5 | Per-classification KMS CMKs for PII + payment + spiritual data; 365-day key rotation | Flows 1,8 | KMS | 3 | High | Security | Phase 3 |
| P3-6 | Migrate offline sync to AppSync Optimistic Concurrency + Amplify DataStore + Delta Sync | Flow 8 (B4) | AppSync + Amplify | 8 | High | Reliability | Phase 3 |
| P3-7 | PostgreSQL RLS policies for multi-tenant lectionary isolation (lectionary_config, lectionary_readings) | Flows 8,1 | PostgreSQL RLS | 3 | Medium | Security | Phase 3 |
| P4-1 | Migrate from REST API to HTTP API v2 (~70% API cost reduction, JWT authorizers native) | All flows | API GW HTTP API | 3 | Medium | Cost Opt. | Phase 4 |
| P4-2 | Graviton2 arm64 migration for all Lambda functions (~20% cost/perf improvement) | All flows | Lambda arm64 | 3 | Medium | Cost Opt. | Phase 4 |
| P4-3 | Redis cache-aside pattern: 30-60s event search, 5-15m popular events, 24h scripture TTLs | Flows 2,8 | ElastiCache Serverless | 4 | Medium | Perf. Eff. | Phase 4 |
| P4-4 | AWS X-Ray distributed tracing + Lambda Powertools across all Lambda and API Gateway flows | All flows | X-Ray + Powertools | 4 | Medium | Oper. Exc. | Phase 4 |
| P4-5 | CloudFront API caching + Origin Shield: separate behaviors for .m3u8 (1-3s) vs .ts segments (24h+) | Flows 2,8 | CloudFront | 3 | Medium | Perf. Eff. | Phase 4 |
| P4-6 | Provisioned Concurrency for payment + scripture paths with Application Auto Scaling | Flows 2,8 | Lambda Prov. Concurrency | 2 | Medium | Perf. Eff. | Phase 4 |
| P4-7 | Easter Computus validation suite: test years 2000-2100, runtime guards for out-of-range years | Flow 8 (B4) | Test framework | 3 | Medium | Oper. Exc. | Phase 4 |
| P4-8 | S3 Intelligent-Tiering for media + Glacier archive for old lectionary data (>9 years) | Flows 2,8 | S3 + Glacier | 2 | Low | Cost Opt. | Phase 4 |
| P4-9 | Reserved Instances + Compute Savings Plans (RDS up to -72%, Lambda up to -17%) | All flows | RDS RI + Savings Plans | 2 | Low | Cost Opt. | Phase 4 |

# 10. Implementation Dependencies

The following dependency relationships must be respected when scheduling remediation work. Attempting items out of sequence will result in rework or incomplete implementations.

## 10.1 Phase 1 Dependencies (No Blockers)

All Phase 1 items can be started immediately in parallel, with the following sequencing recommendation within Phase 1:

Phase 1 Execution Order: P1-2: GuardDuty → P1-3: DLQs → P1-1: WAF → P1-4: JWT/PKCE → P1-5: Stripe Webhooks Rationale: GuardDuty starts immediately (1-day activation). DLQs create the error handling foundation that Phase 2 saga patterns depend on. WAF can run in parallel with DLQs. JWT rotation must precede Stripe key migration to ensure auth tokens are secured before payment secrets are rotated.

## 10.2 Critical Dependency Chains

| Item | Phase | Must Complete Before | Depends On | Rationale |
| --- | --- | --- | --- | --- |
| P1-3 DLQs | Phase 1 | P2-1, P2-2, P2-3, P2-4 | None | All saga patterns and circuit breakers require DLQ destinations for failed state machine runs and async Lambda failures. Building sagas without DLQs creates silent failure risk. |
| P1-4 JWT/PKCE | Phase 1 | P2-6 Stripe Secrets | None | Auth token security must be established before rotating payment secrets. Migrating Stripe keys before PKCE is in place leaves auth endpoints vulnerable. |
| P2-2 Cancellation Saga | Phase 2 | P3-1 Step Functions Migration | P1-3 DLQs, P1-5 Stripe | The cancellation saga is the reference implementation for Step Functions in ROCA. It must be built before the broader Step Functions migration in Phase 3 to establish patterns and CDK constructs. |
| P2-1 RSVP Capacity | Phase 2 | P3-3 RDS Proxy | P1-3 DLQs | RSVP atomic capacity control establishes the PostgreSQL locking patterns. RDS Proxy must be deployed after (not before) atomic operations are validated, to avoid connection pool interference during load testing. |
| P3-1 Step Functions | Phase 3 | P3-2 EventBridge Bus | P1-3 DLQs, P2-2 Saga | Step Functions state machines publish events on transitions. EventBridge integration depends on the Step Functions state machine ARNs being finalized and emitting standardized domain events. |
| P3-4 GIN Indexes | Phase 3 | P4-3 Redis Cache | None | GIN index creation should happen before Redis cache TTLs are configured. Cache-hit rates depend on having accurate search latency baselines, which GIN indexing dramatically changes. |
| P3-5 KMS Encryption | Phase 3 | P3-7 RLS Policies | P2-6 Secrets Manager | Row-level security policies reference the KMS key ARNs used for tenant isolation. KMS CMKs for PII and spiritual data must be established before RLS policies reference them. |
| P4-1 HTTP API Migration | Phase 4 | None (final optimization) | P1-4 JWT/PKCE, P3-2 EventBridge | HTTP API migration changes the API Gateway type, which affects WAF ACL attachment, JWT authorizer configuration, and EventBridge Pipe connections. All upstream dependencies must be stable. |
| P4-9 Reserved Instances | Phase 4 | None (financial commitment) | Phase 1-3 complete | Reserved Instance commitments should only be made after the architecture is stabilized (Phases 1-3 complete), as architectural changes (RDS Proxy, Graviton2, HTTP API) alter the instance type and count requirements. |

# 11. Cost Impact Summary

The following optimizations provide quantifiable cost savings and performance improvements. These savings estimates are based on AWS published benchmarks and pricing comparisons. Actual savings will vary based on usage volume.

| Item | Optimization | AWS Service | Est. Savings | Metric | Phase |
| --- | --- | --- | --- | --- | --- |
| P4-1 | HTTP API migration from REST API | API Gateway HTTP API | ~70% API cost reduction | Per API call cost | Phase 4 |
| P4-2 | Graviton2 arm64 Lambda migration | Lambda arm64 | ~20% cost/performance improvement | Lambda GB-second cost | Phase 4 |
| P4-9 | RDS Reserved Instances (1-year term) | RDS Reserved Instances | Up to -40% vs. On-Demand | RDS instance-hours | Phase 4 |
| P4-9 | RDS Reserved Instances (3-year term) | RDS Reserved Instances | Up to -72% vs. On-Demand | RDS instance-hours | Phase 4 |
| P3-1 | Step Functions (waits zero compute during wait states) | Step Functions Standard | Zero compute during waits | Lambda execution time | Phase 3 |
| P4-3 | Redis cache reduces DB read operations | ElastiCache Serverless | ~60% reduction in RDS read queries | RDS I/O operations | Phase 4 |
| P4-5 | CloudFront caching reduces origin requests | CloudFront + Origin Shield | ~40% reduction in Lambda invocations for cached content | Lambda invocations, API GW calls | Phase 4 |
| P4-8 | S3 Intelligent-Tiering + Glacier archive | S3 IT + Glacier | ~30% storage cost reduction | S3 storage GB-month | Phase 4 |
| P3-3 | RDS Proxy reduces cold connection overhead | RDS Proxy | Reduced Lambda timeout/retry costs | Lambda timeouts, error retries | Phase 3 |
| TOTAL ESTIMATED | Combined platform-wide optimization impact | Multiple services | 35-50% total AWS cost reduction | Monthly AWS spend | P3+P4 |

Recommended Sequencing for Cost Optimization 1. Graviton2 migration (P4-2): Immediate 20% Lambda savings with minimal risk. Apply first within Phase 4. 2. HTTP API migration (P4-1): 70% API Gateway cost reduction. Apply after architecture is stable. 3. Reserved Instances (P4-9): Make 1-year RI commitments first to minimize risk. Upgrade to 3-year after validating architecture stability (no more instance type changes expected). Note: Cost savings estimates assume current architecture continues at baseline load. Growing user base will increase absolute savings proportionally.

# Appendix A: AWS Config Rules for Continuous Compliance

The following AWS Config rules provide continuous compliance monitoring for the remediation items. Deploy these rules as part of the Phase 1 CDK/SAM templates to ensure ongoing coverage after initial implementation.

| Config Rule Name | Description | Related Item | Severity | Remediation Action |
| --- | --- | --- | --- | --- |
| api-gw-associated-with-waf | Checks that API Gateway REST API stages are associated with a WAF WebACL | P1-1 WAF | Critical | Attach WAF WebACL via CDK construct |
| guardduty-enabled-centralized | Checks that Amazon GuardDuty is enabled in the account and region | P1-2 GuardDuty | Critical | Enable GuardDuty via AWS Organizations |
| lambda-dlq-check | Checks that Lambda functions with async invocations have a configured DLQ | P1-3 DLQs | Critical | Add DLQ via Lambda on-failure destination |
| lambda-function-public-access-prohibited | Checks that Lambda resource-based policies do not allow public access | P1-1 WAF | High | Remove public Lambda permissions |
| secretsmanager-rotation-enabled-check | Checks that Secrets Manager secrets have rotation enabled | P2-6 Stripe Keys | High | Enable automatic rotation in Secrets Manager |
| kms-cmk-not-scheduled-for-deletion | Checks that KMS CMKs are not scheduled for deletion | P3-5 KMS | High | Cancel pending KMS key deletion |
| rds-instance-public-access-check | Checks that RDS DB instances do not have public accessibility enabled | P3-3 RDS Proxy | Critical | Disable RDS public access; route via RDS Proxy |
| sqs-dlq-check | Custom rule: checks that SQS queues have a configured DLQ with max receive count <= 5 | P1-3 DLQs | Critical | Configure SQS redrive policy |
| cloudwatch-alarm-action-check | Checks that CloudWatch alarms have at least one alarm action | P1-3 DLQs | High | Add SNS notification to DLQ depth alarms |
| cognito-user-pool-mfa-enabled | Checks that Cognito user pools have MFA enabled | P1-4 JWT | High | Enable MFA in Cognito user pool settings |
| rds-logging-enabled | Checks that RDS instances have logging enabled (error, slow query, general) | P3-3 RDS Proxy | Medium | Enable RDS parameter group logging settings |
| xray-sampling-enabled | Custom rule: checks that X-Ray active tracing is enabled on API Gateway stages | P4-4 X-Ray | Medium | Enable X-Ray active tracing in stage settings |

# Appendix B: CDK/SAM Template Specifications

The following CDK construct and SAM template specifications define the platform-level infrastructure patterns that should be codified as reusable components. These templates enforce Phase 1 remediations consistently across all current and future ROCA flows.

## B.1 WAF WebACL CDK Construct

This CDK construct creates a WAF WebACL with the AWS Managed Rules Common Rule Set, ACFP (Account Creation Fraud Prevention), and rate limiting, then attaches it to a specified API Gateway stage.

// RocaWafConstruct - reusable across all API Gateway stages

export class RocaWafConstruct extends Construct {

constructor(scope: Construct, id: string, props: WafProps) {

const webAcl = new wafv2.CfnWebACL(this, 'RocaWebACL', {

defaultAction: { allow: {} },

rules: [

{ name: 'AWSManagedRulesCommonRuleSet', priority: 1 },

{ name: 'AWSManagedRulesKnownBadInputsRuleSet', priority: 2 },

{ name: 'AWSManagedRulesACFP', priority: 3 },

{ name: 'RateLimit', priority: 4, limit: 2000 }  // per 5 min

]

});

new wafv2.CfnWebACLAssociation(this, 'ApiWafAssoc', {

resourceArn: props.apiStageArn,

webAclArn: webAcl.attrArn,

});

}

}

## B.2 DLQ Lambda Construct

This construct adds a Dead Letter Queue to an existing Lambda function and creates a CloudWatch alarm that fires when the DLQ depth exceeds 1 message.

// RocaDLQConstruct - wraps any async Lambda with DLQ protection

export class RocaDLQConstruct extends Construct {

constructor(scope: Construct, id: string, props: DLQProps) {

const dlq = new sqs.Queue(this, 'DLQ', {

retentionPeriod: Duration.days(14),

encryption: sqs.QueueEncryption.KMS_MANAGED,

});

props.lambda.addEventSource(new destinations.SqsDestination(dlq));

new cloudwatch.Alarm(this, 'DLQAlarm', {

metric: dlq.metricApproximateNumberOfMessagesVisible(),

threshold: 1,

evaluationPeriods: 1,

alarmDescription: `DLQ depth > 0 for ${props.lambda.functionName}`,

});

}

}

## B.3 GuardDuty Enablement SAM Template

This SAM/CloudFormation template enables GuardDuty with all protection plans in a single deployment. Run this template once per account/region as part of the Phase 1 sprint.

AWSTemplateFormatVersion: '2010-09-09'

Resources:

GuardDutyDetector:

Type: AWS::GuardDuty::Detector

Properties:

Enable: true

Features:

- Name: RDS_LOGIN_EVENTS

Status: ENABLED

- Name: LAMBDA_NETWORK_LOGS

Status: ENABLED

- Name: S3_DATA_EVENTS

Status: ENABLED

FindingPublishingFrequency: FIFTEEN_MINUTES

# Appendix C: Batch Report Index

The following table lists all individual AWS Well-Architected Review reports produced across the 4 batches. Each report contains detailed findings, evidence citations, and batch-specific remediation recommendations that support the consolidated findings in this document.

| Batch | Report Title | Flows | Status | Key Findings |
| --- | --- | --- | --- | --- |
| B1 | AWS Well-Architected Framework Review of ROCA New Member Onboarding Flow | Flow 1 | Complete | 15 findings. Established 5 platform-wide gaps: WAF, GuardDuty, DLQs, JWT rotation, Step Functions. First identification of all systemic issues. |
| B2a | AWS Well-Architected Framework Review for ROCA Event Management Flows | Flows 2-3 | Complete | Initial Batch 2 findings: RSVP race conditions, RRULE parsing, Stripe secrets, concurrent booking risks. |
| B2b | AWS Well-Architected Framework Review for ROCA Event Management Flows with Batch 1 Gap Analysis | Flows 2-3 | Complete | Cross-batch gap analysis confirming all Batch 1 platform gaps compound in Batch 2 with payment flows. Escalated WAF/GuardDuty to Critical. |
| B2c | AWS Well-Architected Framework Review for ROCA Event Management Flows: Payment Security, Concurrency, and Operational Resilience Assessment | Flows 2-3 | Complete | Deep-dive on Stripe PCI DSS v4.0 compliance, RSVP SELECT FOR UPDATE fix, webhook verification, and SQS FIFO ordering. 21 total gaps, 40-55 engineering days. |
| B3 | AWS Well-Architected Framework Review for ROCA Middle-Tier Flows: Orchestration, Scheduling, and Notification Architecture | Flows 4-7 | Complete | 80-95 engineering days across P0 (~27 days), P1 (~26 days), P2 (~24 days). SES bounce, FCM v1 migration, cancellation saga, RRULE DST, notification reliability. |
| B4a | AWS Well-Architected Framework Review for ROCA Scripture and Lectionary Flow with Cross-Batch Remediation Strategy | Flow 8 | Complete | Initial Batch 4 analysis: Bible API circuit breaker, GIN indexes, offline sync conflicts, Computus algorithm, RLS policies, reading plan streak integrity. |
| B4b | AWS Well-Architected Framework Review for ROCA Scripture and Lectionary Management Flow with Cross-Batch Remediation Roadmap | Flow 8 | Complete | Final Batch 4 + consolidated cross-batch summary. 30-40 incremental days. Confirmed 240-280 day total platform remediation. Source of the unified roadmap data in this document. |

## C.1 Report Reading Guide

- For Security audit purposes: Start with Batch 1 report (establishes baseline vulnerabilities), then Batch 2c (payment security deep-dive). These two reports contain all Critical security findings.

- For Reliability review: Read Batch 3 report (saga patterns, notification reliability) and Batch 4b (circuit breaker, offline sync). These contain the most complex reliability architectures.

- For Cost optimization planning: Batch 4b contains the consolidated cost impact summary and all four-phase effort estimates. Cross-reference with this unified roadmap's Phase 4 section.

- For Architectural design review: Batch 4b appendix contains the cross-batch severity heatmap showing how each finding evolved across all 4 batches, with evidence citations to AWS documentation.

Document Sign-Off Status: APPROVED ¦ Version: 1.0 ¦ Date: August 2026 This document represents the consolidated engineering leadership decision record for ROCA platform remediation investment across all 8 application flows. The four-phase remediation strategy provides a sequenced, dependency-aware plan that prioritizes systemic platform-level fixes before flow-specific remediations, maximizing ROI on engineering investment. Source: AWS Well-Architected Framework Review ¦ ROCA Church Management Platform ¦ Batches 1-4 ¦ All 8 Flows